## Stage 1 Planning
Stage 1: Planning | Olympic Community of Health
Milestones | Work Steps | Project Areas | [5 empty] | Key Deliverables / Outcomes | ACH Organization | Partnering Provider Organization | Timing
|  | 2A | 2D | 3A | 3B | 3C | 3D |  |  |  | DY2,Q1 | DY2,Q2 | DY2,Q3 | DY2,Q4 | DY3,Q1 | DY3,Q2 | DY3,Q3 | DY3,Q4 | DY4,Q1 | DY4,Q2 | DY4,Q3 | DY4,Q4 | DY5,Q1 | DY5,Q2 | DY5,Q3 | DY5,Q4
Identify work steps and deliverables to implement the transformation activities and to facilitate health systems and community capacity building (HIT/HIE, workforce/practice transformation, and value-based payment), and health equity. (Completion no later than DY 2, Q3) |  | X | X | X | X | X | X
| Participate in the Health Systems Capacity Building Workgroup (AWPHD, UW, HCA, ACHs, DOH) | X | X | X | X | X | X | Plan that prioritizes health system capacity building strategies | Executive Director | None | bar: Timing DY2,Q1 to Timing DY2,Q3
| Design PHBH and CBOSS‡ Change Plans to identify preferred activities to facilitate health systems and community capacity building and health equity | X | X | X | X | X | X | PHBH and CBOSS‡ Change Plan templates | Clinical Transformation Manager | None | bar: Timing DY2,Q1 to Timing DY2,Q3
| Complete PHBH and CBOSS‡ Change Plans | X | X | X | X | X | X | Completed PHBH and CBOSS‡ Change Plans | None | PHBH* and CBOSS^ Implementation Partners
| Review Outcomes and Tactics from submitted PHBH and CBOSS‡ Change Plans related to health systems capacity building and health equity | X | X | X | X | X | X | Review notes | Clinical Transformation Manager | None
| Review Outcomes and Tactics from submitted PHBH and CBOSS‡ Change Plans to identify selected trainings (including health equity training) | X | X | X | X | X | X | List of selected trainings from Implementation Partners | Clinical Transformation Manager | None
| Identify shared training opportunities with other ACHs (including health equity training) | X | X | X | X | X | X | Cross-ACH training inventory | Executive Director | None
| Identify preferred technical assistance vendors from Implementation Partners | X | X | X | X | X | X | OCH Current State Assessment results | Data Lead | None
| Identify interest in shared EHR, EBHR and/or population health management systems | X | X | X | X | X | X | PHBH Change Plan indicates preference, updated annually | None | PHBH* Implementation Partners
For 2020 adopters of integrated managed care: Ensure planning reflects timeline and process to transition to integration of physical and behavioral health including: engage and convene County Commissioners, Tribal Governments, Managed Care Organizations, Behavioral Health and Primary Care providers, and other critical partners (Completion no later than DY 2, Q4) |  | X | bar: Timing DY2,Q3 to Timing DY2,Q4
| Plan Integrated Manages Care (IMC) and Value-Based Payment (VBP) trainings for behavioral health providers with Cascade Pacific Action Alliance (CPAA), Qualis Health and DOH | X | [5 empty] | Plan for trainings | Director of Community and Tribal Partnership, Qualis Health Practice Coach Connector | None
| Host IMC and VBP trainings for behavioral health providers with CPAA, Qualis Health, and DOH | X | [5 empty] | Trainings | Director of Community and Tribal Partnership, Qualis Health Practice Coach Connector | None | bar: Timing DY2,Q4
| Assess behavioral health provider readiness for the transition to IMC | X | [5 empty] | Coaching report from Qualis Health | Qualis Health Practice Coach Connector | None | bar: Timing DY2,Q4
| Select six BH Implementation Partners for in-depth IMC technical assistance from Qualis Health | X | [5 empty] | Six BH Implementation Partners selected to receive technical assistance from Qualis Health on IMC | Qualis Health Practice Coach Connector | None | bar: Timing DY2,Q4
| Participate in SBHO Pathway to 2020: IMC preparatory meetings inclusive of all SBHO-subcontracted agencies, HCA and MCOs | X | [5 empty] | Meetings | Director of Community and Tribal Partnership | None | bar: Timing DY2,Q2 to Timing DY2,Q4
| Participate in SBHO Executive Board Meetings | X | [5 empty] | Meetings | Executive Director | None | bar: Timing DY2,Q1 to Timing DY2,Q4
| Participate in SBHO Advisory Board Meetings | X | [5 empty] | Meetings | Director of Community and Tribal Partnership | None | bar: Timing DY2,Q1 to Timing DY2,Q4
| Participate in SBHO Provider Meetings | X | [5 empty] | Meetings | Director of Community and Tribal Partnership | None | bar: Timing DY2,Q1 to Timing DY2,Q4
| Meet monthly with the SBHO to develop an IMC transition plan for appropriate state and local agencies | X | [5 empty] | IMC transition plan | Executive Director | None | bar: Timing DY2,Q3 to Timing DY2,Q4
Regional self-identified Milestone: Develop recommended Outcomes and Tactics in the PHBH Change Plan that are mutually supportive of the IMC transition |  | X
| Implement VBP arrangements with MCOs (include as a Recommended Tactic in the PHBH Change Plan) | X | [5 empty] | PHBH Implementation Partners select this Tactic in their PHBH Change Plan | None | Select PHBH* Implementation Partners
| Report on value-based metrics that will be in MCO contracts (include as a Recommended Tactic in the PHBH Change Plan) | X | [5 empty] | PHBH Implementation Partners select this Tactic in their PHBH Change Plan | None | Select PHBH* Implementation Partners
‡CBOSS Change Plan is currently under development
*Please refer to the tab named "Partner Lists"
^Please refer to the tab named "Partner Lists"

## Stage 2 Implementation
Stage 2: Implementation | Olympic Community of Health
Milestones | Work Steps | Project Areas | [5 empty] | Key Deliverables / Outcomes | ACH Organization | Partnering Provider Organization | Timing
|  | 2A | 2D | 3A | 3B | 3C | 3D |  |  |  | DY2,Q1 | DY2,Q2 | DY2,Q3 | DY2,Q4 | DY3,Q1 | DY3,Q2 | DY3,Q3 | DY3,Q4 | DY4,Q1 | DY4,Q2 | DY4,Q3 | DY4,Q4 | DY5,Q1 | DY5,Q2 | DY5,Q3 | DY5,Q4
Develop guidelines, policies, procedures and protocols (Completion no later than DY 3, Q2) |  | X | X | X | X | X | X
| Identify Outcomes and Tactics in PHBH and CBOSS‡ Change Plans that may require partners to develop new or improved guidelines, policies, procedures and protocols to implement transformation work; share with PHBH and CBOSS Implementation Partners | X | X | X | X | X | X | List of Outcomes and Tactics in PHBH and CBOSS‡ Change Plans | Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q1
| Review a sample of guidelines, policies, procedures and protocols associated with identified list of Outcomes and Tactics from PHBH and CBOSS Implementation Partners at site visits | X | X | X | X | X | X | List of new promising guidelines, policies, procedures and protocols related to PHBH and CBOSS‡ Change Plan activities | Clinical Transformation Manager | None | bar: Timing DY3,Q1
| Review list of new promising guidelines, policies, procedures and protocols internally and/or with subject matter experts | X | X | X | X | X | X | Evaluation of gaps in guidelines, policies, procedures and protocols | Clinical Transformation Manager, Qualis Health Practice Coach Connector | None
| Share recommendation for refinements of guidelines, policies, procedures, and protocols related to PHBH and CBOSS‡ Change Plans on ORCA | X | X | X | X | X | X | Web links on ORCA | Clinical Transformation Manager | None
| Support PHBH and CBOSS Implementation Partners that request or require assistance in developing new guidelines, policies, procedures and protocols | X | X | X | X | X | X | Practice assessments (e.g., PAT, MeHAF, PCMH-A) and/or action plans | Clinical Transformation Manager, P-TCPi Practice Facilitator, Qualis Health Practice Coach Connector | None
Develop continuous quality improvement strategies, measures, and targets to support the selected approaches/pathways (Completion no later than DY 3, Q2) |  | X | X | X | X | X | X
| Form and maintain a diverse quality improvement (QI) team of clinical and administrative staff with protected time to examine and improve upon clinical outcomes, quality of care, and patient satisfaction (Recommended Tactic in PHBH Change Plan) | X | X | X | X | X | X | PHBH Change Plan progress to date reporting indicates progression of QI implementation, updated biannually | None | Select PHBH* Implementation Partners | bar: Timing DY3,Q1
| Implement reporting policies and practices to ensure complete and timely reporting of Change Plan activities to OCH (Recommended Tactic in PHBH and CBOSS‡ Change Plans) | X | X | X | X | X | X | PHBH and CBOSS‡ Change Plan progress to date and quantitative reporting are complete and timely | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q1
| Provide QI technical assistance and training | X | X | X | X | X | X | Training materials and/or technical assistance | Qualis Health Practice Coach Connector, P-TPCi Practice Facilitator | None
| Develop QI approach (data collection, analysis, and continuous monitoring) to track progress on metrics and project implementation, detailing frequency of measure collection and reporting as well as reporting mechanism(s) | X | X | X | X | X | X | Quality Improvement Plan (QIP) with measure set | Data Lead | None | bar: Timing DY2,Q4
| Work with Performance, Measurement and Evaluation Committee (PMEC) to review QI approach and finalize measure set | X | X | X | X | X | X | Recommended measure set | Data Lead | PMEC ^^ | bar: Timing DY2,Q3 to Timing DY3,Q2
| Establish procedures for the QIP | X | X | X | X | X | X | Site visits and QIP reporting | Clinical Transformation Manager, Program Coordinator | None | bar: Timing DY3,Q1
| Convene PMEC to establish guidelines for ongoing review of reported data | X | X | X | X | X | X | PMEC materials | Data Lead | PMEC^^
Ensure each partnering provider and/or organization is provided with, or has secured, the training and technical assistance resources and HIT/HIE tools necessary to perform their role in the integrated care activities (Completion no later than DY 3, Q4) |  | X
| Review PHBH Implementation Partner readiness from Current State Assessment, completed coaching reports and practice assessments to create Implementation Partner readiness (for integrated care activities) matrix | X | [5 empty] | Implementation Partner readiness matrix | Clinical Transformation Manager, Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator | None | bar: Timing DY3,Q1
| Identify trainings and technical assistance needs for integrated care activities associated with Outcomes and Tactics in Change Plans | X | [5 empty] | Training and technical assistance plan | Clinical Transformation Manager, Director of Community and Tribal Partnership, Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator | None | bar: Timing DY3,Q1
| Recommend available trainings and technical assistance | X | [5 empty] | Communications | Clinical Transformation Manager, Director of Community and Tribal Partnership, Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator | None
| Assist PHBH Implementation Partners in tracking QI projects | X | [5 empty] | QI technical assistance | Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator | None
| Collaborate across-ACHs to contract with vendors for overlapping training needs | X | [5 empty] | Contractual agreements | Executive Director | None | bar: Timing DY3,Q1
| Make trainings available to partners | X | [5 empty] | Training | Clinical Transformation Manager | None
| Participate in trainings | X | [5 empty] | Training | None | PHBH* and CBOSS^ Implementation Partners and interested Shared Change Plan** Partners
| Upload recordings, materials, webinars of trainings on ORCA | X | [5 empty] | Web links on ORCA | Program Coordinator | None
Ensure each member of the care team, participating provider and/or organization is provided with, or has secured, the training and technical assistance resources necessary to follow the guidelines and to perform their role in the approach in a culturally competent manner (Completion no later than DY 3, Q4) |  |  | X |  | X | X
| Provide PHBH and CBOSS Implementation Partners with tools to assess cultural competence and facilitate action planning to address gaps that are identified |  | X |  | X | X |  | Coaching report from Qualis Health, coaching report from P-TCPi, practice assessments, results from Current State Assessment, findings from site visits and QIP reporting | Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator, Director of Community and Tribal Partnership | PHBH* and CBOSS^ Implementation Partners
| Offer QI check-ins to help evaluate progress |  | X |  | X | X |  | QI meeting | Qualis Health Practice Coach Connector, P-TCPi Coach Facilitator | None | bar: Timing DY3,Q3
| Evaluate needs of PHBH and CBOSS Implementation Partners on cultural competency |  | X |  | X | X |  | Coaching report from Qualis Health, coaching report from P-TCPi, practice assessments, results from Current State Assessment, findings from site visits and QIP reporting | Qualis Health Practice Coach Connector, P-TCPi Coach Facilitator, Director of Community and Tribal Partnership | None
| Recommend or offer trainings in cultural competency and related areas to PHBH and CBOSS Implementation Partners and Shared Change Plan Partners |  | X |  | X | X |  | Cultural competency or related trainings | Qualis Health Practice Coach Connector, P-TCPi Coach Facilitator, Director of Community and Tribal Partnership | None
Implement selected strategies/approaches across the core components: 1) Prevention; 2) Treatment; 3) Overdose Prevention; 4) Recovery Supports (Completion no later than DY 3, Q4) |  |  |  | X
| Best practices for opioid prescribing are promoted and used (Required Outcome in PHBH Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by PHBH Implementation Partners, participation of Shared Change Plan Partners | None | PHBH* Implementation Partners* and interested Shared Change Plan Partners **
| Providers are trained to recognize potential for opioid use disorder (OUD) and utilize a standardized protocol for screening and referring these patients (Outcome in PHBH Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by PHBH Implementation Partners, participation of Shared Change Plan Partners | None | Select PHBH* Implementation Partners and interested Shared Change Plan Partners **
| Capacity is built to prevent opioid use disorder (Required Outcome in PHBH Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by PHBH Implementation Partners, participation of Shared Change Plan Partners | None | PHBH* Implementation Partners and interested Shared Change Plan Partners **
| Patients are engaged around prevention of OUD (Outcome in PHBH Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by PHBH Implementation Partners, participation of Shared Change Plan Partners | None | Select PHBH* Implementation Partners and interested Shared Change Plan Partners **
| Public is offered education and awareness around opioid epidemic (Outcome in PHBH Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by PHBH Implementation Partners, participation of Shared Change Plan Partners | None | Select PHBH* Implementation Partners and interested Shared Change Plan Partners **
| Educate clients on safe medication return and disposal programs (also called “drug take back”) (Tactic in CBOSS‡ Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by CBOSS Implementation Partners, participation of Shared Change Plan Partners | None | Select CBOSS^ Implementation Partners and interested Shared Change Plan Partners **
| Raise public awareness programs about opioid misuse and abuse prevention through data and programs such as It Starts with One (Tactic in CBOSS‡ Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by CBOSS Implementation Partners, participation of Shared Change Plan Partners | None | Select CBOSS^ Implementation Partners and interested Shared Change Plan Partners **
| Educate clients on safe storage of opioids (Tactic in CBOSS‡ Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by CBOSS Implementation Partners, participation of Shared Change Plan Partners | None | Select CBOSS^ Implementation Partners and interested Shared Change Plan Partners **
| Naloxone is accessible (Required Outcome in PHBH Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by CBOSS Implementation Partners; participation of Shared Change Plan Partners | None | Select CBOSS^ Implementation Partners and interested Shared Change Plan Partners **
| Full spectrum of best practices for evidence-based care for opioid use disorder is available (Required Outcome in PHBH Change Plan) |  |  | X |  |  |  | Biannual report of progress on this work step and any associated intermediary measures by CBOSS Implementation Partners, participation of Shared Change Plan Partners | None | Select CBOSS^ Implementation Partners and interested Shared Change Plan Partners **
Implement bi-directional communications strategies/interoperable HIE tools to support the care model (Completion no later than DY 3, Q4) | [5 empty] | X
| Explore real-time exchange of health information with partners under the Olympic Digital HIT Commons or other platforms such as PreManage or Consent to Share (Recommended Tactic in PHBH and CBOSS‡ Change Plans) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Integrate dental records into the medical EHR (Tactic in PHBH Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
| Utilize screening tools and protocols to identify client oral health needs and inform appropriate referrals (Tactic in CBOSS‡ Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
| Screen clients for engagement with oral health provider and provide resources/referral as needed (Tactic in CBOSS‡ Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
| Refer individuals needing oral health care to oral health care services (Tactic in CBOSS Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
Implement bi-directional communication strategies/interoperable HIE tools to support project priorities (e.g., ensure team members, including client and family/caregivers, have access to the information appropriate to their role in the team and the care plan) (Completion no later than DY 3, Q4) |  |  | X |  | X
| Explore real-time exchange of health information with partners under the Olympic Digital HIT Commons or other platforms such as PreManage or Consent to Share (Recommended Tactic in PHBH and CBOSS‡ Change Plans) |  | X |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Implement PreManage (Tactic in PHBH Change Plan) |  | X |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
| Providers are notified of patient/client ED visits (Required Outcome in PHBH Change Plan) |  | X |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Streamlined process is in place for information to be shared in a timely manner for shared patients/clients (Required Outcome in PHBH Change Plan) |  | X |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Sign inter-organizational agreements for access to records of referred and/or shared patients/clients (Recommended Tactic in PHBH and CBOSS‡ Change Plan) |  | X |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Establish and document a protocol for convening cross-sector care meetings (Tactic in PHBH Change Plan) |  | X |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
| Implement process to review the PRC (patient review and coordination) list and EDIE feeds, assess patient needs and link patients to community providers (Tactic in PHBH Change Plan) |  | X |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
Implement disease/population‐specific Chronic Care Implementation Plan for identified populations within identified geographic areas, inclusive of identified change strategies to develop and/or improve: • Self‐Management Support • Delivery System Design • Decision Support • Clinical Information Systems (including interoperable systems) • Community‐based Resources and Policy • Health Care Organization (Completion no later than DY 3, Q4) | [6 empty] | X
| Facilitate culture shift across Implementation Partner organizations to prioritize chronic disease prevention and management (Required Outcome in PHBH Change Plan) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Foster and enhance community clinical linkages in each NCC to ensure patients are supported and active participants in their disease management (Required Outcome in the PHBH Change Plan) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Form bi-directional referral system within the Natural Community of Care between clinical and community partner for effective chronic care services; refer to appropriate programs depending on patient profile (Recommended Tactic in the PHBH Change Plan) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
| Provide effective chronic care services to referred clients (Tactic in CBOSS‡ Change Plan) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
Obtain technology tools needed to create, transmit, and download shared care plans and other HIE technology tools to support integrated care activities (Completion no later than DY 3, Q4) |  | X
| Review final PHBH Change Plans and crosscheck with Implementation Partner readiness matrix (for integrated care activities) to identify partner needs | X | [5 empty] | List of partner needs | Clinical Transformation Manager | None | bar: Timing DY3,Q1
| Facilitate workflow mapping with Implementation Partners to assess care gaps in technology | X | [5 empty] | Workflow maps | Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator | None
| Teach and design PDSA (Plan, Do, Study, Act) to address identified care gaps | X | [5 empty] | Coaching report from Qualis Health; coaching report from P-TCPi | Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator | None
| Explore real-time exchange of health information with partners under the Olympic Digital HIT Commons or other platforms such as PreManage or Consent to Share (Recommended Tactic in PHBH and CBOSS‡ Change Plan) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Distribute learnings and updates from PreManage learning collaborative | X | [5 empty] | Tools from PreManage learning collaborative | Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q3
| Provide examples of Releases of Information and best practices regarding compliance with 42 CFR Part II | X | [5 empty] | Examples of Releases of Information | Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q3
| Distribute State consent management workgroup materials to BHA and SUD partners | X | [5 empty] | Output from State consent management workgroup | Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q3
| Convene trainings as needed to support partners to implement tools | X | [5 empty] | Trainings | Qualis Health Practice Coach Connector, Clinical Transformation Manager, Director of Community and Tribal Partnership | None
Monitor state‐level modifications to the 2016 Washington State Interagency Opioid Working Plan and/or related clinical guidelines, and incorporate any changes into project implementation plan (Completion no later than DY 3, Q4) |  |  |  | X
| Attend quarterly WA State Interagency Opioid Workgroup |  |  | X |  |  |  | Workgroup meetings | Director of Community and Tribal Partnership | None | bar: Timing DY2,Q2; Timing DY2,Q4
| Share recommendations from Bree Collaborative Opioid Workgroup |  |  | X |  |  |  | Materials | Director of Community and Tribal Partnership | None | bar: Timing DY2,Q2; Timing DY2,Q4
Establish mechanisms for coordinating care with related community-based services and supports (Completion no later than DY 3, Q4) | [5 empty] | X
| Utilize screening tools and protocols to identify client oral health needs and inform appropriate referrals (Tactic in CBOSS‡ Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
| Facilitate alignment with Access to Baby and Child Dentistry (ABCD) |  |  |  |  | X |  | ABCD coordinator participates in NCC convenings | Director Community and Tribal Partnership | None | bar: Timing DY3,Q1
| Develop strategies, emphasizing care coordination between new and existing dental providers and community-based services and supports (Tactic in CBOSS‡ Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | Executive Director | None | bar: Timing DY3,Q1 to Timing DY3,Q2
| Select partner organizations for local oral health improvement network with Arcora Foundation |  |  |  |  | X |  | List of partner organizations for local health improvement network | Executive Director | None | bar: Timing DY3,Q2 to Timing DY3,Q3
| Screen clients for engagement with oral health provider and provide resources/referral as needed (Tactic in CBOSS‡ Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
Establish mechanisms for coordinating care management plans with related community-based services and supports such as those provided through suported housing programs (Completion no later than DY 3, Q4) |  |  | X
| Standardize identification of and track individuals experiencing homelessness and/or food insecurity needing more efficient management and effective care (Recommended Tactic in PHBH Change Plan) |  | X |  |  |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Select Implementation Partners
| SDOHs are assessed and integrated into standard practice (Required Outcome in PHBH and CBOSS‡ Change Plans) |  | X |  |  |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* and CBOSS^ Implementation Partners
Establish mechanisms, including technology-enabled, interoperable care coordination tools, for coordinating care management and transitional care plans with related community-based services and supports such as those provided through supported housing programs (Completion no later than DY 3, Q4) |  |  |  |  | X
| Explore real-time exchange of health information with partners under the Olympic Digital HIT Commons or other platforms such as PreManage or Consent to Share (Recommended Tactic in PHBH and CBOSS‡ Change Plans) |  |  |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Strengthen clinical-community linkages with schools and early intervention programs (child care, preschools, home visiting) to promote well-child visits and immunizations (Tactic in PHBH Change Plan) |  |  |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
| Conduct coordinated, targeted outreach and engagement to increase well-child visits and immunizations rates (Required Outcome in PHBH Change Plan for primary care) |  |  |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners who have submitted a Primary Care Change Plan
| Provide evidence-based prenatal or early childhood interventions to promote optimal health outcomes (Tactic in CBOSS‡ Change Plan) |  |  |  | X |  |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
Implementation should ensure integration of clinical and community‐based strategies through communication, referral, and data sharing strategies (Completion no later than DY 3, Q4) | [6 empty] | X
| Develop care coordination protocols that include screening, appropriate referral, and closing the loop on referrals to connect specific subpopulations to clinical or community services (Required Outcome in PHBH Change Plan) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Integrate social determinants of health (SDOH) assessments into standard practice (Required Outcome in PHBH and CBOSS‡ Change Plans) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* and CBOSS^ Implementation Partners
| Streamline processes for information to be shared in a timely manner for shared patients/clients (Required Outcome in PHBH Change Plan) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Ensure community-clinical linkages so that patients are supported and are active participants in their disease management (Required Outcome in PHBH Change Plans) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Provide effective chronic care services (Tactic in CBOSS‡ Change Plan) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select CBOSS^ Implementation Partners
| Sign Business Associate Agreements or equivalent with partners involved with the patient’s care to support referrals OR sub-contract with community partners to ensure shared patients/clients receive appropriate services (Recommended Tactic in PHBH and CBOSS‡ Change Plans) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Sign inter-organizational agreements for access to records of referred and/or shared patients/clients (Recommended Tactic in PHBH and CBOSS‡ Change Plans) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Participate in a technology platform that allows necessary patient/client information to be exchanged between the referee and referral organization (Recommended Tactic in PHBH and CBOSS‡ Change Plans) | [5 empty] | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
Provide participating providers and organizations with financial resources to offset the costs of infrastructure necessary to support integrated care activities. (Completion no later than DY 3, Q4) |  | X
| Incentivize value-based payment arrangements with MCOs (Tactic in PHBH and CBOSS‡ Change Plans) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners
| Report on value-based metrics that will be in MCO contracts (Recommended Tactic in PHBH Change Plan) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
| QI methods are used to improve care and care delivery (Required Outcome in PHBH Change Plan) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Form and maintain a diverse QI team of clinical and administrative staff with protected time to examine and improve upon clinical outcomes, quality of care and patient satisfaction (Recommended Tactic in PHBH Change Plan) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
Convene or leverage existing local partnerships to implement project, one or more such partnerships may be convened (Completion no later than DY 3, Q4) -Each partnership should include health care service, including mental health and SUD providers, community-based service providers, executive and clinical leadership, consumer representatives, law enforcement, criminal justice, emergency medical services, and elected officials; identify partnership leaders and champions. Consider identifying a clinical champion and one or more community champions. -Establish a structure that allows for efficient implementation of the project and provides mechanisms for any workgroups or subgroups to share across teams, including implementation successes, challenges, and overall progress. -Continue to convene the partnership(s) and any necessary workgroups on a regular basis throughout implementation phase. |  |  |  | X
| Convene 3CCORP Steering Committee, Prevention Workgroup, Treatment Workgroup and Overdose Prevention Workgroup on a regular basis to guide the work of Project 3A |  |  | X |  |  |  | Semi-annual to monthly 3CCORP meetings, agendas and meeting minutes, regional opioid response plan, completion and maintenance of partnering provider roster | Director of Community and Tribal Partnership | None | bar: Timing DY2,Q2; Timing DY2,Q4
| 3CCORP members present accomplishments at Regional Opioid Summit(s) |  |  | X |  |  |  | Regional Opioid Summit(s) | None | 3CCORP members*** | bar: Timing DY2,Q4
Develop workflows to operationalize the protocol, specifying which member of the care team performs each function, inclusive of when referral to dentist or periodontist is needed (Completion no later than DY 3, Q4) | [5 empty] | X
| Receive technical assistance from Arcora Foundation and/or Qualis Health to assist Implementation Partners in identifying care team members and integrating oral health screening and referral to dentist or periodontist into workflows |  |  |  |  | X |  | Standard operating procedure to screen and refer to an oral health provider identified at site visit | Arcora Foundation and Qualis Health | None | bar: Timing DY3,Q3 to Timing DY3,Q4
| Assess progress on workflow integration at site visit |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | Clinical Transformation Manager | Select PHBH* Implementation Partners
| Oral health education, screening and/or preventive procedures are integrated into care (Required Outcome in PHBH Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Train providers on screening for oral health needs and engagement with oral health provider (Tactic in PHBH Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
Develop a plan to address gaps in the number or locations of providers offering recovery support services, (this may include the use of peer support workers) (Completion no later than DY 3, Q4) |  |  |  | X
| Implement regional survey to identify gaps in the number or locations of providers offering recovery support services |  |  | X |  |  |  | Survey results | Director of Community and Tribal Partnership | None | bar: Timing DY3,Q3
| Identify regional care gaps for referred clients to recovery support services within the planning framework of QI team in PC, SUD and BH clinics to address these gaps |  |  | X |  |  |  | Documented QI strategies for referral process to recovery services | Qualis Health Practice Coach Connector | None
Establish referral relationships with dentists and other specialists, such as ENTs and periodontists (Completion no later than DY 3, Q4) | [5 empty] | X
| Oral health education, screening and/or preventive procedures are integrated into care (Required Outcome in PHBH Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* Implementation Partners
| Train providers on screening for oral health needs and engagement with oral health provider (Tactic in PHBH Change Plan) |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners
Establish a rapid-cycle quality improvement process that includes monitoring performance, providing performance feedback, implementing changes and tracking outcomes (Completion no later than DY 3, Q4) |  |  |  |  | X | X
| Establish procedures for and carry out QIP |  |  |  | X | X |  | Scheduled biannual site visits by OCH staff biannual quantitative and qualitative data submitted by PHBH and CBOSS Implementation Partners | Clinical Transformation Manager, Data Lead | PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q3
| Host OCH Performance, Measurement and Evaluation Committee (PMEC) meetings to review PHBH and CBOSS Implementation Partner data |  |  |  | X | X |  | Quarterly PMEC materials and minutes | Data Lead | PMEC^^ | bar: Timing DY3,Q3
| Implement reporting policies and practices to ensure complete and timely Change Plan reporting |  |  |  | X | X |  | PHBH Change Plan progress to date and quantitative reports | Clinical Transformation Manager | None
| Assist PHBH Implementation Partners in tracking QI |  |  |  | X | X |  | QI technical assistance | Qualis Health Practice Coach Connector, P-TCPi Coach Facilitator | None
Engage with payers in discussion of payment approaches to support access to oral health services (Completion no later than DY 3, Q4) | [5 empty] | X
| Facilitate Implementation Partners to establish connection with apparently successful bidders of dental managed care contracts |  |  |  |  | X |  | Communications | Executive Director | None
| Meet with future successful bidders of dental managed care contracts to discuss potential financial and technical support of oral health integration in primary care |  |  |  |  | X |  | Meetings | Executive Director | None
Regional self-identified milestone: Ensure communication with, resource sharing for, and reporting requirements of PHBH and CBOSS Implementation Partners are streamlined, transparent and minimally burdensome while holding them accountable to implementation |  | X | X | X | X | X | X
| Work with CSI (contracted vendor) to develop online platform for communication, resource sharing and reporting | X | X | X | X | X | X | ORCA | Clinical Transformation Manager | None | bar: Timing DY2,Q2 to Timing DY3,Q1
| Ensure Shared Change Plan Partners are registered on ORCA | X | X | X | X | X | X | Registered list of partners on ORCA | Program Coordinator | None | bar: Timing DY2,Q3
| Develop strategy to increase traffic and activity on ORCA | X | X | X | X | X | X | Communications plan | Communications and Development Coordinator | None | bar: Timing DY3,Q1
| Develop streamlined qualitative and quantitative reporting templates on ORCA for bi-annual reporting | X | X | X | X | X | X | Online reporting templates | Clinical Transformation Manager, Data Lead, CSI | None | bar: Timing DY3,Q1
| Solicit feedback on ORCA from PHBH, CBOSS and Shared Change Plan Partners | X | X | X | X | X | X | Feedback forms | Program Coordinator | None | bar: Timing DY3,Q3
Regional self-identified milestone: Align monitoring of implementation progress of MTP with other ACHs |  | X | X | X | X | X | X
| Contribute to cross-ACH repository of intermediary metrics to monitor implementation | X | X | X | X | X | X | List of metrics and their specifications | Data Lead | None | bar: Timing DY2,Q4
| Review and potentially refine OCH intermediary metrics with members of the PMEC to identify opportunities for alignment with other ACHs | X | X | X | X | X | X | List of metrics and their specifications | Data Lead | None | bar: Timing DY3,Q1
Regional self-identified milestone: Health equity considerations are incorporated in implementation of Outcomes and Tactics |  | X | X | X | X | X | X
| PHBH and CBOSS Implementation Partners and Shared Change Plan Partners are surveyed regularly regarding health equity strengths and gaps; gaps are addressed | X | X | X | X | X | X | Regional health equity data | Data Lead, Director of Community and Tribal Partnership | None | bar: Timing DY2,Q2
| Review patient/client data by subpopulations to identify and track inequities (Tactic in PHBH and CBOSS‡ Change Plans) | X | X | X | X | X | X | Biannual report of progress on this work step and any associated intermediary measures | None | PHBH* and CBOSS^ Implementation Partners
| Regional health equity survey results are summarized and presented to the OCH Board, Committees, Natural Communities of Care convenings and staff meetings | X | X | X | X | X | X | Presentations | Data Lead, Director of Community and Tribal Partnership | None | bar: Timing DY2,Q3
Regional self-identified milestone: Proactively engage community-based organizations, Tribes, and the beneficiaries of services to ensure that their voice guides and informs the decision making of the Olympic Community of Health |  | X | X | X | X | X | X
| Establish the Community and Tribal Advisory Committee (CTAC) and meet no less than semi-annually | X | X | X | X | X | X | CTAC meeting calendar | Director of Community and Tribal Partnership, Communications and Development Coordinator | None | bar: Timing DY3,Q1
| Determine appropriate sector representation and convene CTAC | X | X | X | X | X | X | CTAC charter | Director of Community and Tribal Partnership | None | bar: Timing DY2,Q4
| Provide written reports and/or recommendations to the OCH Board and staff to summarize strengths and gaps in social justice and health equity in the work of the MTP | X | X | X | X | X | X | Reports recommendations | Director of Community and Tribal Partnership | CTAC
‡CBOSS Change Plan is currently under development
*Please refer to the tab named "Partner Lists"
^Please refer to the tab named "Partner Lists"
**Please refer to the tab named "Partner Lists"
^^Please refer to the tab named "Partner Lists"
***Please refer to the tab named "Partner Lists"

## Stage 3 Scale and Sustain
Stage 3: Scale and Sustain | Olympic Community of Health
Milestones | Work Steps | Project Areas | [5 empty] | Key Deliverables / Outcomes | ACH Organization | Partnering Provider Organization | Timing
|  | 2A | 2D | 3A | 3B | 3C | 3D |  |  |  | DY2,Q1 | DY2,Q2 | DY2,Q3 | DY2,Q4 | DY3,Q1 | DY3,Q2 | DY3,Q3 | DY3,Q4 | DY4,Q1 | DY4,Q2 | DY4,Q3 | DY4,Q4 | DY5,Q1 | DY5,Q2 | DY5,Q3 | DY5,Q4
Increase use of technology tools to support integrated care activities by additional providers/organizations (Completion no later than DY 4, Q4) |  | X | bar: Timing DY4,Q4
| Explore real-time exchange of health information with partners under the Olympic Digital HIT Commons or other platforms such as PreManage or Consent to Share (Recommended Tactic in PHBH and CBOSS‡ Change Plans) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Explore a common or interoperable EHR or EBHR (Tactic in PHBH Change Plan) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Explore a shared population health management system within Natural Community of Care (Tactic in PHBH Change Plan) | X | [5 empty] | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners and interested Shared Change Plan Partners ** | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
Expand the model to additional communities and/or partner organizations (Completion no later than DY 4, Q4) |  |  | X | bar: Timing DY4,Q4
| Build relationships with stand-alone SUD providers who have not yet participated in practice transformation |  | X |  |  |  |  | Communications and meetings | Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator, Director of Community and Tribal Partnership | None | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Encourage Implementation Partners to expand on the list of selected Tactics and target populations in the PHBH and CBOSS‡ Change Plans that will result in reduced unnecessary ED utilization |  | X |  |  |  |  | PHBH and CBOSS‡ Change Plans include additional Tactics and/or target populations in annual updates | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Scale fully implemented Outcomes and Tactics in PHBH and CBOSS‡ Change Plans |  | X |  |  |  |  | PHBH and CBOSS‡ Change Plans indicate “Scale and Sustain” as status of progress of select Outcomes | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
Increase scale of activities by adding partners and/or reaching new communities under the current initiative (e.g. to cover additional high needs geographic areas), as well as defining a path forward to deploy the partnership's expertise, structures, and capabilities to address other yet‐to‐emerge public health challenges (Completion no later than DY 4, Q4) |  |  |  | X | bar: Timing DY4,Q4
| Convene Regional Opioid Summit(s) for existing partners as well as new partners |  |  | X |  |  |  | Regional Opioid Summit roster | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
| Continue efforts to attend and present at local meetings, coalitions and councils to identify new partners that have not yet engaged and offer targeted invitations to bi-annual Natural Community of Care Convenings, 3CCORP workgroups and/or Opioid Summit(s) |  |  | X |  |  |  | Participation of new partners in OCH-hosted events, committees and workgroups | Director of Community and Tribal Partnership | None | bar: Timing DY3,Q3 to Timing DY4,Q4
| Continue to monitor regional data to identify high needs geographic areas for prevention, treatment, and overdose prevention to address potential inequities in access to care and outcomes |  |  | X |  |  |  | Identification of high-need areas | Data Lead | None | bar: Timing DY4,Q3
| Identify new local efforts to address the opioid public health crisis to share expertise and resources |  |  | X |  |  |  | Roster of regional coalitions and efforts | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q3
Increase scope and scale, expand to serve additional high-risk populations, and add partners to spread approach to additional communities (Completion no later than DY 4, Q4) |  |  |  |  | X | X | bar: Timing DY4,Q4
| Explore operating a mobile dental clinic |  |  |  |  | X |  | Biannual report of progress on this work step and any associated intermediary measures | None | Peninsula Community Health Services | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Coordinate with a mobile dental clinic (Tactic in PHBH and CBOSS‡ Change Plans) |  |  |  |  | X |  | PHBH and CBOSS‡ Change Plans indicate progress towards this work step, updated biannually | None | Select PHBH* and CBOSS^ Implementation Partners and interested Shared Change Plan Partners ** | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Expand on the list of selected Tactics and target populations in the PHBH and CBOSS‡ Change Plans that will result expansion of access to oral health |  |  |  |  | X |  | PHBH and CBOSS‡ Change Plans include additional Tactics and/or target populations in annual updates | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Scale fully implemented Outcomes and Tactics in PHBH and CBOSS‡ Change Plans |  |  |  |  | X |  | PHBH and CBOSS‡ Change Plans indicate “Scale and Sustain” as status of progress of select Outcomes | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Form Local Improvement Networks to enhance oral health access in partnership with the Arcora Foundation |  |  |  |  | X |  | MOU between Arcora and OCH | Clinical Transformation Manager; Executive Director | None
| Enroll new partners on ORCA to enable access to best practice resources and building partnership with partners |  |  |  | X | X |  | Expanded members on ORCA | Program Coordinator | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Deepen partner engagement, continue outreach efforts to invite new partners to convenings and trainings |  |  |  | X |  |  | Convening/training participant lists | Director of Community and Tribal Partnership | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Expand on the list of selected Tactics and target populations in the PHBH and CBOSS‡ Change Plans that will result in improved access and quality of reproductive, maternal and child supports and services |  |  |  | X |  |  | PHBH and CBOSS‡ Change Plans include additional Tactics and/or target populations in annual updates | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Scale fully implemented Outcomes and Tactics in PHBH and CBOSS‡ Change Plans |  |  |  | X |  |  | PHBH and CBOSS‡ Change Plans indicate “Scale and Sustain” as status of progress of select Outcomes | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
Increase scale of approach, expand to serve additional high‐risk populations, include additional providers and/or cover additional high needs geographic areas, to disseminate and increase adoption of change strategies that result in improved care processes and health outcomes (Completion no later than DY 4, Q4) | [6 empty] | X | bar: Timing DY4,Q4
| Expand on the list of selected Tactics and target populations in the PHBH and CBOSS‡ Change Plans that will result in better chronic disease prevention and management | [5 empty] | X | PHBH and CBOSS‡ Change Plans include additional Tactics and/or target populations in annual updates | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Scale fully implemented Outcomes and Tactics in PHBH and CBOSS‡ Change Plans | [5 empty] | X | PHBH and CBOSS‡ Change Plans indicate “Scale and Sustain” as status of progress of select Outcomes | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Enroll new partners on ORCA to enable access to best practice resources and building partnership with partners | [5 empty] | X | Expanded members on ORCA | Program Coordinator | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Deepen partner engagement, continue outreach efforts to invite new partners to convenings and trainings | [5 empty] | X | Convening/training participant lists | Director of Community and Tribal Partnership | None | bar: Timing DY3,Q4; Timing DY4,Q4
Identify new, additional target providers/organizations (Completion no later than DY 4, Q4) |  | X | bar: Timing DY4,Q4
| Submit additional Change Plan types (e.g. Primary Care partner submitting Behavioral Health Change Plan once integration is implemented) | X | [5 empty] | Additional Change Plans | None | Select PHBH* Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Enroll new partners on ORCA to enable access to best practice resources and building partnership with partners | X | [5 empty] | Expanded members on ORCA | Program Coordinator | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Deepen partner engagement, continue outreach efforts to invite new partners to convenings and trainings | X | [5 empty] | Convening/training participant lists | Director of Community and Tribal Partnership | None | bar: Timing DY3,Q4; Timing DY4,Q4
Employ continuous quality improvement methods to refine the model, updating model and adopted guidelines, policies and procedures as required (Completion no later than DY 4, Q4) |  | X | X | X | X | X | X | bar: Timing DY4,Q4
| Submit data to OCH | X | X | X | X | X | X | PHBH and CBOSS‡ Change Plan progress to date and quantitative reporting are complete and timely | None | PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Convene OCH Performance, Measurement and Evaluation Committee (PMEC) meetings to review Implementation Partner data | X | X | X | X | X | X | PMEC materials and minutes | Data Lead | PMEC^^ | bar: Timing DY3,Q3; Timing DY4,Q1; Timing DY4,Q3
| Communicate performance to Implementation Partners | X | X | X | X | X | X | Performance reports/dashboard, site visit materials | Clinical Transformation Manager, Data Lead | None | bar: Timing DY3,Q3; Timing DY4,Q1; Timing DY4,Q3
| Identify opportunities for improvement and develop/implement strategies to support partners | X | X | X | X | X | X | Site visit materials | Clinical Transformation Manager, Qualis Health Practice Coach Connector, P-TCPi Practice Facilitator | None | bar: Timing DY3,Q3; Timing DY4,Q1; Timing DY4,Q3
| Continuously employ QI approach to track progress on metrics and project implementation | X | X | X | X | X | X | Monitoring reports | Clinical Transformation Manager, Data Lead | PMEC^^ | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Convene PMEC to review measures and refine approach based on emerging best practices | X | X | X | X | X | X | PMEC materials and minutes | Data Lead | PMEC^^ | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Employ QI methods to improve care and care delivery (Recommended Tactic in PHBH Change Plan) | X | X | X | X | X | X | PHBH Change Plan indicates “Scale and Sustain” as status of progress of select Outcomes | None | PHBH* Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
Review and apply data to inform decisions regarding specific strategies and action to be spread to additional settings or geographical areas (Completion no later than DY 4, Q4) |  |  |  | X | bar: Timing DY4,Q4
| Update data monitoring reports with most recently available data |  |  | X |  |  |  | Opioid data summaries | Data Lead | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Discuss new data and possible strategy and/or spread opportunities and with 3CCORP and PHBH and CBOSS Implementation Partners |  |  | X |  |  |  | Meeting materials/minutes | Director of Community and Tribal Partnership | 3CCORP*** and PHBH* and CBOSS^ Implementation Partners | bar: Timing DY4,Q2; Timing DY4,Q4
| Discuss data updates with 3CCORP |  |  | X |  |  |  | Meeting materials/minutes | Data Lead, Director of Community and Tribal Partnership | None | bar: Timing DY4,Q2; Timing DY4,Q4
| Update provider specific data reports |  |  | X |  |  |  | Provider specific data reports | Data Lead | None | bar: Timing DY4,Q4
| Discuss data with PHBH and CBOSS Implementation Partners to inform decisions about strategies and/or spread |  |  | X |  |  |  | Meeting materials | Clinical Transformation Manager | None | bar: Timing DY4,Q1; Timing DY4,Q3
| Present data at annual Regional Opioid Summit(s) |  |  | X |  |  |  | Regional Opioid Summit agenda, slide deck, summary report | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
| Monitor data to track and address health equity in Outcomes |  |  | X |  |  |  | Equity tracking | Data lead, Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
Provide ongoing supports (e.g., training, technical assistance, learning collaboratives) to support continuation and expansion (Completion no later than DY 4, Q4) |  | X | X |  | X | X | bar: Timing DY4,Q4
| Include topical breakout sessions and/or training at Natural Community of Care convenings | X | X |  | X | X |  | Convenings | Clinical Transformation Manager, Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Collaborate with Qualis Health to continue coach facilitator services | X | X |  | X | X |  | Meetings | Clinical Transformation Manager, Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q2
| Provide progress reports to PHBH Implementation Partners related to Eight Change Concepts of the Patient Centered Medical Home Principles | X | X |  | X | X |  | Coaching report from Qualis Health | Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Continue to utilize ORCA as a resource repository; keep resources updated and include emerging best practices | X | X |  | X | X |  | Timely posts on ORCA | Program Coordinator | None | bar: Timing DY3,Q3 to Timing DY4,Q4
| Utilize results from QI process with PHBH and CBOSS Implementation Partners to inform TA and training support | X | X |  | X | X |  | Coaching report from Qualis Health | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Evaluate and update training plan based on feedback from QI process to respond to evolving partner needs | X | X |  | X | X |  | Training Plan | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY4,Q1; Timing DY4,Q3
| Continue to support partners in advancement of health equity through QI activities, evaluation and the procurement of resources to assist progress | X | X |  | X | X |  | Equity tracking | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY4,Q4
Provide or support ongoing training, technical assistance, learning collaborative platforms, to support shared learning, spread and continuation, and expansion of successful change strategies (e.g., the use of interoperable Clinical Information Systems by additional providers, additional populations, or types of information exchanged) (Completion no later than DY 4, Q4) | [6 empty] | X | bar: Timing DY4,Q4
| Include breakout sessions and/or training in chronic disease prevention and control at Natural Community of Care convenings | [5 empty] | X | Convenings | Clinical Transformation Manager, Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Collaborate with Qualis Health to continue coach facilitator services | [5 empty] | X | Meetings | Clinical Transformation Manager, Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q2
| Provide progress reports to Implementation Partners related to Eight Change Concepts of the Patient Centered Medical Home Principles | [5 empty] | X | Coaching report from Qualis Health | Qualis Health Practice Coach Connector | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Continue to utilize ORCA as a resource repository; keep resources updated and include emerging best practices | [5 empty] | X | Timely posts on ORCA | Program Coordinator | None | bar: Timing DY3,Q3 to Timing DY4,Q4
| Utilize results from QI process with PHBH and CBOSS Implementation Partners to inform TA and training supports | [5 empty] | X | Coaching report from Qualis Health | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Evaluate and update training plan based on feedback from QI process to respond to evolving partner needs | [5 empty] | X | Coaching report from Qualis Health | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY4,Q1; Timing DY4,Q3
| Continue to support partners in advancement of health equity through QI activities, evaluation and the procurement of resource to assist progress | [5 empty] | X | Equity tracking | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY4,Q4
| Develop regional Behavioral Health Academy to train workforce in transitioning to integrated care | [5 empty] | X | Training modules | Qualis Health Practice Coach Connector | None | bar: Timing DY4,Q4
Provide or support ongoing training, technical assistance, and community partnerships to support spread and continuation of the selected strategies/approaches (Completion no later than DY 4, Q4) |  |  |  | X | bar: Timing DY4,Q4
| Convene Regional Opioid Summit(s) to deliver training and identify technical assistance needs and new partnership opportunities |  |  | X |  |  |  | Regional Opioid Summit(s) | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
| Collaborate with University of Washington to implement 6 Building Blocks for improved opioid prescribing in clinics in the region |  |  | X |  |  |  | Clinics participate in 6 Building Blocks | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q1
| Collaborate with DOH to coordinate training for providers to become waivered for MAT |  |  | X |  |  |  | MAT training | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
| Collaborate with StopOverdose.org to provide TA and training to recognize and appropriately respond to opioid related overdoses |  |  | X |  |  |  | Overdose response training | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
| Continue to utilize ORCA as a resource repository; keep resources updated and include emerging best practices |  |  | X |  |  |  | Timely posts on ORCA | Program Coordinator | None | bar: Timing DY3,Q3 to Timing DY4,Q4
| Utilize results from QI process with PHBH and CBOSS Implementation Partners to inform TA and training supports |  |  | X |  |  |  | Coaching report from Qualis Health | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY3,Q4; Timing DY4,Q4
Leverage regional champions and implement a train-the-trainer approach to support the spread of best practices (Completion no later than DY 4, Q4) |  | X | bar: Timing DY4,Q4
| Identify regional champions | X | [5 empty] | List of regional champions | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY3,Q4
| Connect regional champions with Natural Communities of Care to share best practices with other providers | X | [5 empty] | Presentations at Natural Community of Care Convenings | Qualis Health Practice Coach Connector, Clinical Transformation Manager | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Interview regional champions to learn promising practices | X | [5 empty] | Interview notes | Qualis Health Practice Coach Connector, Communications and Development Coordinator | None | bar: Timing DY4,Q1
| Facilitate opportunities for regional champions to spread best practices | X | [5 empty] | Presentations, resources on ORCA, newsletters | Program Coordinator, Communications and Development Coordinator | None | bar: Timing DY4,Q4
Identify and encourage arrangements between providers and MCOs that can support continued implementation of the Project(s) beyond DY5 (Completion no later than DY 4, Q4) |  | X | X | X | X | X | X | bar: Timing DY4,Q4
| Implement value-based payment arrangements with MCOs (Tactic in PHBH and CBOSS‡ Change Plans) | X | X | X | X | X | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Report on value-based metrics that will be in MCO contracts (Recommended Tactic in PHBH Change Plan) | X | X | X | X | X | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
Convene and support platforms to facilitate shared learning and exchange of best practices and results to date (e.g., the use of interoperable HIE by additional providers providing treatment of persons with OUD) (Completion no later than DY 4, Q4) |  | X |  | X | bar: Timing DY4,Q4
| Convene 3CCORP Steering Committee and Workgroups |  |  | X |  |  |  | Meeting materials | Director of Community and Tribal Partnership | None | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Establish real-time exchange of health information between MAT prescriber and SUD provider for bidirectional referral and care coordination for shared patient with OUD under the Olympic Digital HIT Commons or similar technology platform | X |  | X |  |  |  | E-referral technology platform | None | Select PHBH* Implementation Partners | bar: Timing DY4,Q3
| Scale Olympic Digital HIT Commons or similar technology platform to new partners and use cases | X |  | X |  |  |  | E-referral technology platform participant list | None | Select PHBH* Implementation Partners and interested Shared Change Plan Partners ** | bar: Timing DY4,Q4
Identify and resolve barriers to financial sustainability of Project(s) activities post-DSRIP (Completion no later than DY 4, Q4) |  | X | X | X | X | X | X | bar: Timing DY4,Q4
| Implement value-based payment arrangements with MCOs (Tactic in PHBH and CBOSS‡ Change Plans) | X | X | X | X | X | X | Biannual report of progress on this work step and any associated intermediary measures | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q2; Timing DY4,Q4
| Educate lawmakers, State partners, and payers on barriers to sustainability due to scope of practice, billing, coding and HIT constraints | X | X | X | X | X | X | Meet with ACH EDs, legislators, MCOs and State partners | Executive Director | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Advocate with other ACHs for Medicaid reimbursement codes that will directly support Change Plan Outcomes and Tactics | X | X | X | X | X | X | Meet with ACH EDs, legislators, MCOs and State partners | Executive Director | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Support statewide efforts to address rural workforce shortages | X | X | X | X | X | X | Information sharing with WSHA and WA Health Workforce Sentinel Network | Executive Director | None | bar: Timing DY3,Q4; Timing DY4,Q4
| Explore an all-payer collaborative | X | X | X | X | X | X | Meet with MCO and commercial payer partners | Executive Director | None | bar: Timing DY4,Q2
| Explore rural global payment strategies | X | X | X | X | X | X | Meet with HCA and hospital partners | Executive Director | None | bar: Timing DY4,Q1
Regional self-identified milestone: MAT Providers and SUD Providers are closely networked for referral and coordination of treatment for shared patients with opioid use disorder |  | X |  | X | bar: Timing DY4,Q4
| Deepen engagement with MAT prescribers and SUD providers and convene together to facilitate coordination | X |  | X |  |  |  | Meeting materials | Director of Community and Tribal Partnership | None | bar: Timing DY3,Q4; Timing DY4,Q4
Regional self-identified milestone: Develop and share regional standards of practice for referral and treatment of opioid use disorder (use Bree Collaborative Opioid Use Disorder Treatment Report and Recommendations) |  | X |  | X | bar: Timing DY4,Q4
| 3CCORP Treatment Work Group to develop regional standards of practice | X |  | X |  |  |  | Regional standards of practice for treatment of OUD | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q2
| Disseminate regional standards of practice | X |  | X |  |  |  | Regional standards of practice for treatment of OUD are shared region-wide | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
| Regional standards of practice for referral and treatment of opioid use disorder are reviewed annually by the 3CCORP Treatment Workgroup to update to current best practices | X |  | X |  |  |  | Annual review and update as needed based on current best practices | Director of Community and Tribal Partnership | None | bar: Timing DY4,Q4
Regional self-identified milestone: Expand integration of SDOHs and health equity into physical health and behavioral health practice |  | X | X | X | X | X | X | bar: Timing DY4,Q4
| Encourage Implementation Partners to expand on the list of selected Tactics in the PHBH Change Plan that integrate SDOH screening and appropriate referral into practice | X | X | X | X | X | X | PHBH Change Plan includes additional Tactics in annual updates | None | Select PHBH* Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Encourage Implementation Partners to expand on the list of target subpopulations in the PHBH Change Plan to include populations experiencing the greatest health disparities | X | X | X | X | X | X | PHBH Change Plan includes additional target subpopulations in annual updates | None | Select PHBH* Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
| Scale fully implemented Outcomes and Tactics in PHBH and CBOSS Change Plans related to SDOH and health equity | X | X | X | X | X | X | PHBH and CBOSS‡ Change Plans indicate “Scale and Sustain” as status of progress of select Outcomes | None | Select PHBH* and CBOSS^ Implementation Partners | bar: Timing DY3,Q4; Timing DY4,Q4
‡CBOSS Change Plan is currently under development
*Please refer to the tab named "Partner Lists"
^Please refer to the tab named "Partner Lists"
**Please refer to the tab named "Partner Lists"
^^Please refer to the tab named "Partner Lists"
***Please refer to the tab named "Partner Lists"

## Partner Lists
Partner Lists - Olympic Community of Health
* The current list of PHBH Implementation Partners is below. Some organizations may have submitted multiple PHBH Change Plans, such as the hospital health systems. Remaining Tribal Partners may choose to become an Implementation Partner in 2019.
1. Beacon of Hope, Safe Harbor Recovery
2. Bogachiel and Clallam Bay Primary Care Clinics
3. CHI Franciscan Harrison Medical Center, Primary Care and Family Residency
4. Discovery Behavioral Health
5. Forks Community Hospital
6. Jamestown Family Health Clinic
7. Jefferson Healthcare
8. Kitsap Children's Clinic
9. Kitsap Medical Group
10. Kitsap Mental Health Services
11. Kitsap Recovery Center
12. North Olympic Healthcare Network
13. Olympic Medical Center and Physicians
14. Olympic Personal Growth
15. Peninsula Behavioral Health
16. Peninsula Community Health Services
17. Port Gamble S'Klallam Tribe
18. Reflections Counseling Services Group
19. Sophie Trettevick Indian Health Center
20. Suquamish Tribe (not yet confirmed)
21. West End Outreach Services
22. West Sound Treatment Center
^This is a potential list of Community Based Organization Social Services Implementation Partners who have been active in their Natural Communities of Care and will most likely submit a CBOSS Change Plan.
1. Clallam Health and Human Services
2. First Step
3. Jefferson County Public Health
4. Kitsap Community Resources
5. Kitsap Public Health District
6. OESD 114
7. OlyCap
8. Olympic Area Agency on Aging
9. Olympic Peninsula Healthy Communities Coalition
10. Port Angeles Fire Department
11. United Way of Kitsap
12. YMCA of Kitsap and Pierce Counties
^^ This is a list of organizations represented by members on the Performance, Measurement, and Evaluation Committee.
1. Department of Social and Health Services
2. Jefferson County Public Health
3. Jefferson Healthcare
4. Kitsap Medical Group
5. Kitsap Mental Health Services
6. Molina Health Care
7. Olympic Personal Growth
8. Peninsula Community Health Services
9. Salish Behavioral Health Organization
10. Suquamish Tribe
** Shared Change Plan Partners self-identified during Natural Community of Care convenings. The Shared Change Plan is an overarching document outlining the NCC partners’ commitment to collaborating on key strategies. The Shared Change Plans provide a filter for each Change Plan. Nearly all partnering providers attended at least one NCC Convening and was provided an opportunity to provide input into and sign onto the Shared Change Plan as follows: We agree to cooperate with other agencies and Tribes/Indian Health Care Providers in our Natural Community of Care to implement the activities of the Shared Change Plan. We will share lessons learned and best practices with partners. We will participate with a sincere spirit of collaboration, an open mind, willingness to listen, mutual respect, and a commitment to doing the right work.
Clallam Natural Community of Care Shared Change Plan Partners
1. Bogachiel and Clallam Bay Primary Care Clinics
2. City of Port Angeles Fire Department
3. First Step Family Support Center
4. Forks Community Hospital
5. North Olympic Healthcare Network
6. Olympic Areas Agency on Aging
7. Olympic Medical Center
8. Olympic Personal Growth
9. Peninsula Behavioral Health
10. Planned Parenthood of the Greater Northwest and Hawaiian Islands
11. Port Angeles Police Department
12. Reflections Counseling Services Group
13. Sophie Trettevick Indian Healthcare Center
14. West End Outreach Services
Kitsap Natural Community of Care Shared Change Plan Partners
15. Agape Unlimited
16. Amerigroup Washington
17. Harrison Health Partners Primary Care Clinics
18. Harrison Medical Center
19. Kitsap Children's Clinic
20. Kitsap County Division of Aging and Long Term Care
21. Kitsap Medical Group
22. Kitsap Mental Health Services
23. Kitsap Public Health Department
24. Kitsap Recovery Center
25. Molina Healthcare
26. Northwest Washington Family Medical Residency
27. Peninsula Community Health Services
28. Planned Parenthood of the Greater Northwest and Hawaiian Islands
29. West Sound Treatment Center
30. YMCA of Pierce and Kitsap Counties
Jefferson Natural Community of Care Shared Change Plan Partners
31. Beacon of Hope, Safe Harbor Recovery
32. Community Health Improvement Plan
33. Discovery Behavioral Health
34. Jefferson County
35. Jefferson Public Health
36. Olympic Areas Agency on Aging
37. Olympic Community Action Programs
38. Salish Behavioral Health Organization
***Three County Coordinated Opioid Response Project (3CCORP) has representation from tribes/Indian Health Care Providers, health care service, including mental health and SUD providers, community-based service providers, executive and clinical leadership, consumer representatives, law enforcement, criminal justice, emergency medical services, public health, syringe exchange, MCOs, lived experience, community members and elected officials.
Currently active:
1. American Indian Health Commission of WA State
2. Amerigroup
3. Bogachiel Clinic
4. Bremerton Fire
5. Cedar Grove Counseling Services
6. Center for Opioid Safety Education
7. Clallam County Commissioner
8. Clallam County Drug Court
9. Clallam County Health and Human Services
10. Clallam County Jail
11. Clallam County Prosecuting Attorney
12. Clallam County Public Health Officer
13. Community Health Plan of Washington
14. Coordinated Care
15. Department of Early Learning
16. Discovery Behavioral Health
17. Evergreen Treatment Services
18. First Step Family Support Center
19. Forks Community Hospital
20. Harrison Health Partners/Doctor's Clinic
21. Harrison Medical Center Emergency Department
22. Health Care Authority
23. Individuals in Recovery
24. Jamestown S'Klallam Family Health Clinic
25. Jefferson County Commissioner
26. Jefferson County Public Health
27. Jefferson County Public Health Officer
28. Jefferson Healthcare
29. Kaiser Permanente
30. Kitsap County Commissioner
31. Kitsap County Coroner
32. Kitsap County Human Services
33. Kitsap County Public Health
34. Kitsap County Public Health Officer
35. Kitsap County Prosecutor’s Office
36. Kitsap Mental Health Services
37. Kitsap Recovery Center
38. Klallam Counseling
39. Lower Elwha Tribe
40. Makah Tribe
41. Molina
42. North Olympic Healthcare Network
43. NW WA Family Medicine Residency
44. Olympic College
45. Olympic Community Action Programs
46. Olympic Educational Service District 114
47. Olympic Medical Center
48. Olympic Medical Physicians
49. Olympic Peninsula Health Services
50. Olympic Personal Growth Center
51. Peninsula Behavioral Health Services
52. Peninsula College
53. Peninsula Community Health Services
54. Peninsula Community Health Services Dentist
55. Peninsula Community Health Services Pharmacist
56. People's Harm Reduction Allicance
57. Port Angeles CAN
58. Port Angeles Police Department
59. Port Gamble S’Klallam Tribe
60. Poulsbo City Mayor
61. Quileute Tribe
62. Reflections Counseling Center
63. Safe Harbor Recovery Center
64. Salish Behavioral Health Organization
65. Sophie Trettevick Indian Health Center (Makah)
66. StopOverDose
67. Suquamish Tribe Human Services
68. Suquamish Police Department
69. Suquamish Wellness Center
70. U of WA Alcohol and Drug Abuse Institute
71. WA Governor's Office
72. WA State Department of Health
73. West End Outreach Services
74. West Sound Treatment Center
Potential partners not yet committed or engaged:
75. Agapé
76. Bainbridge Island Police Department
77. Bainbridge Island Fire Department
78. Bremerton Mayor
79. Clallam County Drug Court
80. Clallam County Sheriff Office
81. Clallam County Superior Court
82. Hoh Tribal Police Department
83. Hoh Wellness Center
84. Jefferson County Drug Court
85. Jefferson County Jail
86. Jefferson County Sheriff Office
87. Kitsap Children's Clinic
88. Kitsap County Sheriff’s Office Jail
89. Kitsap County Superior Court
90. Kitsap County Drug Court
91. Makah Tribal Police Department
92. North Kitsap Family Practice
93. Ostrich Bay Exchange
94. Port Gamble S’Klallam Police Department
95. Quileute Police Department

## Master Acronym List
Master Acronym List for Implementation Plan Work Plan
Olympic Community of Health
3CCORP | Three County Coordinated Opioid Response Project
ACH | Accountable Community of Health
AWPHD | Association of Washington Public Hospital Districts
BH | Behavioral Health
BHA | Behavioral Health Agency
CBOSS | Community Based Organizations and Social Services
CPAA | Cascade Pacific Action Alliance
CTAC | Community and Tribal Advisory Committee
DOH | Department of Health
EBHR | Electronic Behavioral Health Record
ED | Emergency Department
EDIE | Emergency Department Information Exchange
EHR | Electronic Health Record
HCA | Health Care Authority
HIT | Health Information Technology
IMC | Integrated Managed Care
MAT | Medication Assisted Treatment
MCO | Managed Care Organization
MeHAF | Maine Health Access Foundation
MOU | Memorandum of Understanding
MTP | Medicaid Transformation Project
NCC | Natural Community of Care
OCH | Olympic Community of Health
ORCA | Olympic Reporting and Community Activities (OCH-developed online, electronic reporting and community platform)
OUD | Opioid Use Disorder
PAT | Practice Assessment Tool
PC | Primary Care
PCMH-A | Patient Centered Medical Home Assessment
PDSA | Plan, Do, Study, Act
PHBH | Physical Health Behavioral Health
PMEC | Performance Measurement and Evaluation Committee
P-TCPi | Pediatric Transforming Clinical Practice Initiative
PTSH | Practice Transformation Support Hub
QI | Quality Improvement
QIP | Quality Improvement Plan
SBHO | Salish Behavioral Health Organization
SDOH | Social Determinants of Health
SUD | Substance Use Disorder
TA | Technical Assistance
UW | University of Washington
VBP | Value Based Payment
WSHA | Washington State Hospital Association